## Stanley Glenn Brucal
No. | Defense No. | Faculty Name | Comment Type | Comment | Status
1 | 1 | Stanley Glenn Brucal | For Revisions | Reposition Logout Button
2 | 1 | Stanley Glenn Brucal | For Revisions | Email verification for pasword resets
3 | 1 | Stanley Glenn Brucal | For Revisions | Include "others" in your category
4 | 1 | Stanley Glenn Brucal | For Revisions | Relable "publish and new case" to "publish and create new case"
5 | 1 | Stanley Glenn Brucal | For Revisions | Missing: Referral Page
6 | 1 | Stanley Glenn Brucal | For Revisions | Error notification in creating a case (missing fields)
7 | 1 | Stanley Glenn Brucal | For Revisions | Simplify color scheme
8 | 1 | Stanley Glenn Brucal | For Revisions | Groupings of cases: Case, My Case, All
9 | 1 | Stanley Glenn Brucal | Additional Requirements | Completeness of functions in proposal design /features
10 | 1 | Stanley Glenn Brucal | Additional Requirements | Data compliance (acknowledgement will do)
11 | 2 | Stanley Glenn Brucal | For Revisions | Inclusion of powers for referred cases
12 | 2 | Stanley Glenn Brucal | For Revisions | Limiting of recipients to included parties (to students for new cases; to faculty for referred case)
13 | 2 | Stanley Glenn Brucal | For Revisions
14 | 2 | Stanley Glenn Brucal | For Revisions | labels for creating a case (notes part)
15 | 2 | Stanley Glenn Brucal | For Revisions | prescribed data format / creating cases
16 | 2 | Stanley Glenn Brucal | Additional Requirements | With pending deficiencies for defense -1
17 | 1 | Einstein Yong | Comment Type | Mouse pointer is not accurate when hovered in Import Page
18 | 1 | Einstein Yong | For Revisions | Adding case (Professor) - Category should have "other"
19 | 1 | Einstein Yong | For Revisions | Professor log-in doesn't have a "student-adding"
20 | 1 | Einstein Yong | For Revisions | Should be able to involve professors and students
21 | 1 | Einstein Yong | For Revisions | Consider solving the color methapor
22 | 1 | Einstein Yong | For Revisions | As a professor log-in, I can't see the history of close cases
23 | 1 | Einstein Yong | Additional Requirements | Reports not yet working
24 | 2 | Einstein Yong | Comments | Pls. address all concerns from first defense
25 | 2 | Einstein Yong | For Revisions | Color issue
26 | 2 | Einstein Yong | For Revisions | Proper sorting of cases
27 | 2 | Einstein Yong | For Revisions | The -1 issue
28 | 2 | Einstein Yong | For Revisions | Issue about case referral
29 | 2 | Einstein Yong | For Revisions | Difficulty is retrieving previous cases and answered cases
30 | 2 | Einstein Yong | For Revisions | Why can't I view my answered cases
31 | 2 | Einstein Yong | Additional Requirements | Problem in reference, the message should also be forwarded to the reason referred to
32 | 2 | Einstein Yong | Additional Requirements | Recipient could not search for some student/faculty
33 | 2 | Einstein Yong | Additional Requirements | History of archiving needs improvement
34 | 1 | Sergio Peruda, Jr. | For Revisions | No Admin Account Yet
35 | 1 | Sergio Peruda, Jr. | For Revisions | XD/Pd Account *Display of descemetion (It should be based in log-in user level)
36 | 1 | Sergio Peruda, Jr. | For Revisions | Notification for import
37 | 1 | Sergio Peruda, Jr. | For Revisions | Imported Subject
38 | 1 | Sergio Peruda, Jr. | For Revisions | There are some modules that require removal of fields
39 | 1 | Sergio Peruda, Jr. | Additional Requirements | Documentation (Changes should be reflected)
40 | 2 | Sergio Peruda, Jr. | For Revisions | User's Manual *Since there are some changes in the process
41 | 2 | Sergio Peruda, Jr. | For Revisions | Case Thread
42 | 2 | Sergio Peruda, Jr. | For Revisions | Redundant field (for referring a case)
43 | 2 | Sergio Peruda, Jr. | For Revisions | Viewing of cases (by # of days or by priority)
44 | 1 | Leonardo Samaniego, Jr. | For Revisions | Report for faculty/adviser
45 | 1 | Leonardo Samaniego, Jr. | For Revisions | Rename "hot" into a more appropriate term or remove "hot" and leave the two choices in the selection
46 | 1 | Leonardo Samaniego, Jr. | For Revisions | revise content of the category in the creation of new case
47 | 1 | Leonardo Samaniego, Jr. | For Revisions | include all cases (current/close) in an archive/ any repository
48 | 2 | Leonardo Samaniego, Jr. | Comments | Address all issues previously commented in the midterm defense (i.e. cursor configuration)
49 | 2 | Leonardo Samaniego, Jr. | For Revisions | in filing cases, field for category (others) cannot be filled in with different case
50 | 2 | Leonardo Samaniego, Jr. | For Revisions | in filing cases, field for subjects cannot be filled in with new subject
51 | 2 | Leonardo Samaniego, Jr. | Additional Requirements | Include number of attempts/trials in the change of password
52 | 2 | Leonardo Samaniego, Jr. | Additional Requirements | Include all cases (current/close) in an archive/ any repository